## 24-25
Exec = Chair, Vice Chair, Treasurer and CEO supported by ZA |  |  |  |  | CPHW (Gov Group)
AHW LPCs STRATEGY – Key Objectives for workplan 24-25 |  |  |  |  | May 16th 2024
Work Strand | Subsection | Objective/ Desired Outcome | Lead | Milestones | May 2024 Update H&W
Governance | Market Entry | Respond to all contract applications on time | ZA / FL / Regs Group | Respond within required timelines and update database | G
| Finance | Payplus managed payroll instigated Autumn 2023 | Review efficiency during year |  | G
|  | Set Xero up with App for scanning invoices | FL / Treasurers with Accountants | Meeting in February 2024 to align Xero / SAGE both LPCs and look at App - speak to Accountants | A
|  | Budget agreed and circulated Feb for each next financial year - split into Joint and individual taking account of NHS Funds available | Exec & Finance Group | Plan and priorities - Sept / Oct each year - Nov 2023 meeting Execs & Finance Groups - then draft budget in Jan 2024 for April onwards - using CPE template | G
|  | Treasurer reports and financial governance - reviewed alternate meetings as minimum. New Pack implemented | Treasurer & Exec & finance group | New Finance Pack implemented by April 2024 | A
|  | Accounts & Annual Report prepared for each AGM in September | FL/ EC / Treasurers / ZA | Docs to Accountant mid May, 6 week completion - queries within 2 weeks and first draft within 4 weeks, final within 6 weeks - end June. AR ready for Sept. Accounts shared LPC July meeting. Sent out for sign off by early August for min 30 days ahead Sept AGMs. | A
|  | Meet with Accountants Feb 24 - May | Treasurers & FL | February 2024 agree what needed for accounts and timelines as above (Met in May) | G
|  | Full governance review of banking processes to ensure governance robust | Exec & Finance Group | Reviewed November 2023 - Follow up Feb 2024 | G
|  | NHS / non levy monies monitored and utilised against MOU requirements | FL / Treasurers | Reviewed November 2023 - Follow up Feb 2024 | G
| Internal Governance | CPA and CPHW Joint Execs | Execs & ZA | Meeting | G
|  | CPE - LPC RAG status complete and follow actions annually | ZA / Exec | Avaiting Governance Documents and new RAG | R
|  | New CPE Governance Documents Implementation | Execs & ZA | Review annually February / March | G
|  | Members capability & capacity & ways of working. | ZA / FL | Complete biannually and for new members | A
|  | Director Insurance & ICO and Employers Insurance and CPE insurance in place |  | In place | G
|  | Training & Conference attendance as needed - |  | CPE Conferences - Activity Courses, Pharma, CPPE | G
| Subgroups | Services / Exec and subgroups to operate at LPC Meetings - approve ToR and update as CPE advice comes through | All | ToR provisional in place - review Jan 2024 - then with new CPE governace packs | A
| Internal Communications | Ensure clear communications within Team and handovers for leave / cover – set up and review action logs. Ensure minutes of meetings are completed, checked and added to website as agreed in timely fashion | Team | Monday.com | A
| Record keeping | Maintain version control of all documents in use and file in agreed location accessible to the team | Team | Default - admin Box - enter all final documents monthly. Share drives for documents requiring multiple access. Database maintained daily | G
| Risks & Issues | Maintain a log and follow up weekly, escalate as necessary. | ZA / Team | Action Log in place to add Escalated Risks Log - shared drive - using Monday.com | G
|  | Maintain record of stakeholder and contractor queries – use to inform best practice and FAQ support |  | Stakeholder mapping and database to be completed for March 2023 | G
| SLAs - Services | Review all old & new SLAs & RAG plus hold quarterly meetings with local service commissioners. Website checks | EC / LNH | Review annually and when come up for renewal | G
Work Strand | Subsection | Objective/ Desired Outcome | Lead
Contractor Support | Communications | website CPE format completed - annually check all pages for accuracy. All to be trained on how to maintain it by end April 2024 | SKS | Trained by end April 2024 | A
|  | Social media - X / facebook / LinkedIn/ Blog | SKS |  | G
|  | Communication Plan - all channels: General, PQS, PCNs, CPCF etc | Team |  | A
|  | Newsletters - for AHW | Team | Biweekly general comms and bimonthly Service Comms | G
|  | Visits & Individual support & leadership training - set up visit and call cycle at some LPC meetings. Some targetting and agree key messaging | Team | To be reinstated - calls / visits mid to late 2024 | A
| Training and development | Resources - Services pack update to one pagers | EC / LNH | External Pack to be completed by July | A
|  | Events -2 a year min - 'don’t leave money on table' and make things simple - claiming guide etc | Team | Review option for series on tutorials online | A
|  | Recorded training bite size and Activity PDP |  |  | A
|  | Implementation & increased activity | EC / LNH | Review Data weekly / monthly - contact referrers or Contractors as needed | A
|  | Peer support - CPD revalidation | Team | Summer 2024 | R
|  | New Contract / PQS / New Services - PCARP - resources | Team | PCARP main focus | G
Work Strand | Subsection | Objective/ Desired Outcome | Lead
| Local Service Commissioner meetings | arrange quarterly local commissioners and review SLA - to increase value | EC/ LNH |  | G
Stakeholder Management | Mapping & priorities (Healthcare, Social Care, Academia, Negotiating Bodies, Commissioners, Regulatory, Pharma, MP, Councillors, Third Sector, LMC, GP Federation, PCNs, patient bodies, charities, social prescribing) | National & Regional - relationships | FL |  | G
|  | Stakeholder mapping | EC / LNH/ FL / ZA | Complete database by end April 2024 | A
|  | Local - ICS, PLACE, PCN - meeting attendance and briefing documents / bids etc |  |  | G
|  | Local - CC, ICB NHSEi, CPCL - meeting attendance and briefing documents / bids etc |  |  | G
PCN Leads – CP and within PCN – support and link working - or any new links
| Communication Plan | Newsletters and packs for stakeholders including MPs | Team |  | G
|  | Press & Media - to be proactive and utilise CPE resources | Team |  | A
|  | Develop Marketing Plan | Team |  | A
| Engagement | Representation on appropriate groups | EC / FL |  | A
|  | Influencing & Negotiating at all levels (training as needed) | Team | Review PDPs for training needs | R
| Structure | Keep under review ICS mergers etc - if planned then consider merger LPCs | FL / Exec | Review annually | G
|  | Transformation work | FL | As required | G
| Digital | IT, databases, websites etc | SKS + Team | Daily / Weekly | G
| Reviewing plans/ strategies / journals | Collate summarise and disseminate information | LNH / EC / FL | Undertake annually April - June | R
| Patients | Healthwatch & Patient Communications | ZA / Team |  | G
Work Strand | Subsection | Objective/ Desired Outcome | Lead
Service & Pathway Opportunities Development | Essential Services | Support meeting core and resolution issues | Team |  | A
|  | DMS - support | Team |  | A
|  | PQS - support and communications | Team | not supported re CPE stance 23-24 . 24-25 TBC | R
| Advanced Services | NMS, CPCS, Flu, Covid, GPCPCS, EDCPCS, SS, BP, Pharmacy First, OC etc | EC / LNH | See main priorites below | G
| Locally Commissioned Services | Retention | LNH / EC |  | G
|  | Development add ons | EC / LNH | extended care decommissioned | A
| Data sets for meetings | Agree useful data to review quarterly and produce Services Report minimum alternate LPC Meetings | LNH / EC | Services Report alt LPC Meetings | A
| Opportunities | Understand priorities | EC / LNH |  | G
|  | Develop services and business cases - DES | EC / LNH |  | A
|  | Local - PCN - generic | EC / LNH | n/a CW | A
| Implementation | Services Pack to replace PCN pack | EC / LNH | January 2024 - update twice a year or as needed | G
|  | New Services | EC / LNH |  | G
|  | National - local application | EC / LNH |  | G
| Working with CHS | Subcontracting, opportunity appraisals | EC / LNH |  | A
| Council | PH other services - generic | EC / LNH |  | A
| Project Management | Service work and data crunching and dissemination - Training for LNH | LNH / EC | During 2024 | A
Work Strand | LPC Plan Strategy | CPA and CPHW
| Workforce | Career, training, retention, cross sector - facilitation of information sharing | FL | Ongoing as needed | G
Local LPC Activities | Main Joint priorites - Pharmacy First | Identified Autumn 2023 | EC | Jan-March 2024 | G
| Main joint priorites - BP | Identified Autumn 2023 | EC | Nov 2023 - Jan 2024 | G
| Main joint priorities - OC | Identified Autumn 2023 | EC | Nov 2023 - Jan 2024 | G
| Main local priorities - Integration | Identified Autumn 2023 | FL | Jan - June 2024 | G
| Local Relationships | Local - ICB, PLACE, PCN - meeting attendance and briefing documents / bids etc Local - CC, ICB, NHSEi - meeting attendance and briefing documents / bids etc | FL / EC / LNH | As arranged | G
|  | Issue resolution | ZA | As arranged
|  | Contractor – Stakeholder relationship support, intervention, | FL |  | G
|  | Develop network of Regional / Area Managers within Contractor base | ZA / Team | Include in biweekly comms | A
|  | Link to other Workforce / HCPs – Dentist / Optometrists for example | FL / EC | Annual meetings - LMC - more frequent | R
|  | CPCL New Leads – links into 8c role and digital transformation | FL / EC | Weekly meetings | G
|  | Network of patient groups and Pharma and third sector |  | Minimum annually | G
|  | Specialist Groups – eg Vaccinations / AMR etc | FL / EC | As arranged | G
HR | Clyde & Co templates in use | All in place and updated as needed - portal checked quarterly | FL / ZA | Quarterly check and update as necessary | G
| Objectives | Relate to Work plan areas and LPC priorities | FL for Team (Chair/ Exec for CEO) | Add priorites to work plan | G
| Reviews | Objective setting and annual review Jan - February ahead of joint Exec meeting. Interim reviews in Autumn ahead of November joint Exec meeting | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | A
| Training and development | PDP as part of Reviews / Interim Reviews | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | A

## Main Priorities 24-25
Subsection | Objective/ Desired Outcome | Lead | Milestones / Timelines | Each LPC Budget | Each LPC NHS Funds Budget | Activities | RAG | Last Q 23-24 | 1st Q 24-25 | 2nd Q 24-25 | 3rd Q 24-25 | Last Q 24-25
Finance | Treasurer reports and financial governance - reviewed alternate meetings as minimum. New Pack implemented | Treasurer & Exec & finance group | New Finance Pack implemented by April 2024 | Within staff hours and Exec Meetings (2 joint meetings a year outside of LPC Meetings) £2,000 | N/A |  | G |  | Reviewd and acted upon
Internal Governance | New CPE Governance Documents Implementation & LPC Transformation & ToR | Execs & ZA | Review annually February / March | Within staff hours and WG Meetings (2 a year outside of LPC Meetings) £2,000 | N/A |  | G |  | Set up and ToR etc adopted
Main Joint priorites - Pharmacy First | Identified Autumn 2023 | EC & WG | Jan-March 2024 | Team normal hours | £10,000 each inc WG time | See CPCS / PhF AGM outouts | G | Services Pack and set up working group | Second meetings planned in and priorities set
Main joint priorites - BP | Identified Autumn 2023 | EC & WG | Nov 2023 - Jan 2024 | Team normal hours | £10,000 each inc WG time | See BP AGM outputs | G | Services Pack and set up working group | Second meetings planned in and priorities set
Main joint priorities - OC | Identified Autumn 2023 | EC & WG | Nov 2023 - Jan 2024 | Team normal hours | £5,000 - 6,000 each inc WG time |  | G | Services Pack and set up working group | Second meetings planned in and priorities set
Main local priorities - Integration | Identified Autumn 2023 | FL & WG | Jan - June 2024 | Team normal hours | £10,000 each LPC - PCN Lead support | See Fuller AGM outputs | A | Outputs from AGMs and set up working group | H&W Integration and joint plan being worked on
Clyde & Co templates in use | All in place and updated as needed - portal checked quarterly | FL / ZA | Quarterly check and update as necessary | Team normal hours | N/A |  | G |  | Most recent docs in place and LH offered pension option
Objectives | Relate to Work plan areas and LPC priorities | FL for Team (Chair/ Exec for CEO) | Add priorites to work plan | N/A | N/A |  | G |  | Set in Autumn and confirmed January for 24-25
Reviews | Objective setting and annual review Jan - February ahead of joint Exec meeting. Interim reviews in Autumn ahead of November joint Exec meeting | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | £1,000 for meetings | N/A |  | A | Next meeting Nov 2024 - draft interim reviews
Training and development | PDP as part of Reviews / Interim Reviews | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | £2,000 for training | £2-3,000 Pharmacy Connect - LPN funds each |  | A | PDP set 24-25 - interim review November

## AGM Outputs
Fuller Team of Teams - Integration
Workstream – Fuller Team of Teams | Current Position | Aim within 1-2 years | Actions required | Delivering on the actions.
How and when?
People | Independent contractor model GP & CP | Portfolio working | Explain the why to support managing change and overcome resistance. | Briefing document – Pharmacy Offer by end January 2024
| Workforce issues | Flexible workforce | ICB to support attracting workforce resilience and training. | Briefing document – Contractors by end January 2024
|  | Better use skill mix | Upskilling to improve skill mix usage. | Link with Training Hub and Workforce Lead Farzana – share opportunities for cross sector and training – regular meetings to be set up and follow up actions
Promote training available and look at gaps to facilitate additional training using NHS Funds – e.g. clinical skills
Communication | Relationships need improving | SPOC CP and GP | Clear lines of communication and standard way of presenting patient information (NEWS style) | Training & Resources & IT development
| Media releasing information too early before ready. | Clear updates on service availability to referrers | Two-way feedback – constructive and regular and acted upon. | Regular meetings to be set up – links into PLACE and ICB.
| Lack of transparency over strategies in ICB. |  | Keep communicating at all levels | Quarterly meetings with Lynda and Charmaine.
Arrange follow session for PCN / ICB and CP plus Herefordshire Meeting
Develop External Newsletter – quarterly
Contribute to GP Connect Bulletins
Promote Pharmacy Connect Platform
Ambition for integration | Disconnect between ambition and reality | Full understanding and plan of vision and part CP can play | CP representation & integration with PCNs | Encourage CP to share top line BCPs in exchange for PCN BCPs. Review option for CP Leads in PCNs or PLACE
BCP – system / PCN level integration
Finance | Disparity in funding | Appropriate funding | Funding for training workforce and improve skills. Support succession planning. | Outside of our control other than for local services
Digital | Lack of interoperability of IT systems | Single IT system / records | IT Integration – common record – mechanism to write to records - | Outside of our control nationally
Locally influence digital team to move pharmacy up the priority list
Primary Care inclusion | GP centric other HCPs excluded | Joint Plan for whole ICS / PCNs | Develop workstreams and plans across PCN/ PLACE etc | Work for inclusion in groups and decision making.
|  |  | Openness re patient safety and system learning around incidents | Provider Collaborative should include all Providers – seek support from Lynda for inclusion
Maintain links with PLACE clinical forums
Patient | Clearer messaging at the right time – not too far before or after. | Patient led services and pathways | Develop mechanism for patient communication. Media / press / social media etc. | Set up links with ICB communications team – for patient communications and posters etc
| Lack of understanding as to what pharmacies offer in general and specifically at individual pharmacies | Patient safety key | Engage and involve in plans | Produce options for Blog, social media, media and press – utilise CPE / ICB materials where available. Aim for blog / social media posts monthly and media / press annually
Meet with Healthwatch quarterly
Services | Service offers lacks consistency and hence impacts confidence to refer. | Funding model needs reviewing | Produce clear processes and links to existing pathways | Link with PLACE and ICB to embed CP services into local pathways – OC, BP, PhF initially during 2024
| Services do not always link into local pathways | Clear pathways | Core CP services – integrate, referral and feedback loops
National services to reduce local variation and CP meet requirements
Pharmacy First as norm
Consistency of provision
Pharmacy First
Workstream – GPCPCS & Pharmacy First | Current Position | Aim within 1-2 years | Actions required | Delivering on the actions.
How and when?
Referral process | Inconsistency | Right referrals via right pathway and well managed | Training on using platforms | Pharmacy First – from end January 2024 – CPCS and CCS will be linked – avoiding the confusion with Extended Care.
| EMIS integrated system | Consistent numbers to make BAU – act on feedback. | Referral process / IT funded | Develop / use CPE comms / briefings for patients, practices, ICB and relaunch from February
| Not linked to online triage systems like AccuRx | Triage for some conditions to improve referral appropriateness | Link with CCS / Pharmacy First | Understand the data available
| Some success and most PCNs have engaged | Aim for double current numbers within 12 months (1200) | Data | Encourage sign up to Pharmacy First, OC and BP asap and by mid-January 2024
| Some ARRS roles undertake minor illness triage |  | Clear pathways | Provide briefing for care navigation training and an induction pack
| Process for feedback not consistent |  |  | Confirm IT for referral arrangements with ICB for 2024 – by end January
Some inappropriate referrals (off licence etc / confusion with extended care)
Service delivery in CP | Variable on a daily basis difficult to manage | All pharmacies working the same way and checking IT platform and NHSmail regularly during the day | Consistent service and links with CCS | Pharmacy First will bring the two services together.
| Return to GP if not picked up | Confident and competent delivery of service and onward referrals etc. Clear information on IT system which goes back to GP. Act on feedback. | Processes embedded | Ensure Pharmacy Connect used
| Workforce capacity issues. Ensure whole team and locums know service |  | Use of Pharmacy Connect | Set up feedback mechanism from PCNs / practices on new combined service – from February 2024
Ensure CP well briefed and pack updated as needed – January 2024
IT access to GP Connect – record information – details to follow
Communications | Feedback loop needs improving | Good links GP – CP | Data evaluation and sharing | Recheck contact numbers and emails ahead of February 2024 and re-issue
| Phones / emails need to be consistently responded to | Case studies / success stories | Clear pathways | Develop template for feeding back information and who tells patient the outcome – January 2024
|  | Better IT connections | Clear feedback loops and acting on issues and sharing successes
Patient engagement | Patients difficult to contact – patient and not opting to contact pharmacy. Patient goes to wrong pharmacy. | Patients understand the service – benefits and how it works | Promotion to patients – posters in surgeries / screens etc – manage expectations | Promotion to patients – ICB action & posters
|  | Press / media / posters | Health library for patients for selfcare | Care navigation support aligned to practice toolkit – ICB action
Briefing for reception teams – service and what to say to patients referred – give pharmacy contact details so patient can contact directly
Healthwatch engagement
Practice engagement | Variable especially in rural areas. Lot of change in CP has reduced confidence in provision. Perception bounce backs % higher than is (<10%) | Better support from dispensing practices | Continued support for IT integrated approach and better information post event | ICB action
|  | Consistent level of referrals & quality |  | CP completion IT platform and GP Connect patient record viewing
Robust training and part of induction new staff
Pharmacy engagement | Huge amount of change and pressure in CP. | Full understanding of the process and benefits of service. Good communication with CP. All (f2f) pharmacies offer CPCS and DSPs where possible | Training all staff and locums | Training support – ICB and LPC – clinical skills and CPPE etc
|  | Robust training and part of induction new staff & locums | Messaging to patients clear to avoid bounce backs | CP staff briefing and locum engagement – LPC – more regular checks of emails & IT platform - action for January / February 2024
|  |  | Better communications with practices | Use of Pharmacy Connect
All checking systems and acting on referrals as part of BAU daily processes
BP Service
Workstream – BP Service | Current Position | Aim within 1-2 years | Actions required | Delivering on the actions.
How and when?
Surgery Process | Use home monitoring rather than ABPM – disconnect | Referral IT solution | Adapt process to link with local pathways and needs | Agree a pragmatic approach where ABPM not taken up by patient – suggest home monitoring to take results to GP when make required appointment.
| NICE levels not same as GP levels used for action | Increase referrals |  | Ensure CP understands changes in skill mix and 14 reading only ABPM required now – 2 per hour – in pack January 2024
| Untapped potential to refer to CP. Consent issue to resolve |  |  | Set up mechanism for referral by March 2024
Pharmacy Process | Referral / notification to GP – not always as per spec. | Include home monitoring as option for patients not wanting ABPM – local and national push | Include home monitoring as option for patients not wanting ABPM – local and national push – influence a change | Develop pragmatic approach where ABPM not taken up by patient CP suggest home monitoring to take results to GP when make required appointment. NB wherever possible use ABPM.
| Can use other members of the team and some referral levels changed. |  | Smart BP App recommended for patients – home monitoring as well | Ensure CP understands changes in skill mix and 14 reading only ABPM required now – 2 per hour – in pack January 2024
| Not all signed up are providing and of those not all doing ABPM. | Include Rx management in future and more Tiers – like health check | Ensure good GP – CP relationships
Funding for more BP and ABPM kit
All pharmacies signed up delivering service.
Funding for offsite option
IT Solution | Easy route to refer in required and for reporting back | Robust IT for whole process including referrals | Common IT platform | Outside of our control – push for it nationally
Communication | There is find a pharmacy providing service online option. Advertising available just on hold until CP ready – part of PCARP | Advertising to patients and parts of system and links to pathways. | Share wins and case studies | Collect case studies and share anon – ongoing - quarterly
|  |  | Advertising to patients | Review data and share performance – ongoing - monthly
|  |  | Review materials available to advertise / inform patients and primary care teams. | Review materials and recommend resources – develop if a gap – early 2024
|  |  | Form of words for patients for each scenario where link back to surgery required – timeframe for surgery / home BP / ABPM – | Communicate pragmatic approach for CP to support
|  |  | Remember – language and health literacy re patient information | Form of words and timeframe for feedback linked to specification – for early 2024
Feedback to surgery | Inconsistent | Clear useful feedback
| Vaccination clinics doing BP – caused some concerns as false high reading and ABPM follow not completed | Uniformity of service and feedback information
Interest.