## BAU 25-26
Exec = Chair, Vice Chair, Treasurer and CEO supported by ZA |  |  |  |  | CPHW (Gov Group) | CPHW January 2025 | CPHW - reviews due May 2025 & September 2025 & Janaury 2026
AHW LPCs STRATEGY – Key Objectives for workplan 25-26 (carried over from 24-25) |  |  |  |  | May 16th 2024 | 2025-01-01 | 2025-05-01
Work Strand | Subsection | Objective/ Desired Outcome | Lead | Milestones | May 2024 Update H&W | January 2025 and updated for 25-26 | 2025-05-01
Governance | Market Entry | Respond to all contract applications on time | ZA / FL / Regs Group | Respond within required timelines and update database | G | G
| Finance | Payplus managed payroll instigated Autumn 2023 | Review efficiency during year |  | G | G
|  | Meeting in April / May 2025 to review process going forward and any joint approach between CPA and CPHW | FL / Treasurers with Accountants | Meeting to be arranged and discussed at Joint Exec to agree way forward and office support to reduce Treasurer costs. To include possible joint account and software accounting packages | A | A
|  | Budget agreed and circulated Feb for each next financial year - split into Joint and individual taking account of NHS Funds available | Exec & Finance Group | Plan and priorities - Sept / Oct each year - Nov meeting Execs & Finance Groups - then draft budget in Jan LPC meetings for April onwards - using CPE template | G | G
|  | Treasurer reports and financial governance - reviewed alternate meetings as minimum. New Pack implemented | Treasurer & Exec & finance group | New Finance Pack implemented by April 2024 and reviewed January 2025. Checklist to form part of the self - assessment process 2-4 times a year | A | G
|  | Accounts & Annual Report prepared for each AGM in September | FL/ EC / Treasurers / ZA | Docs to Accountant mid May, 6 week completion - queries within 2 weeks and first draft within 4 weeks, final within 6 weeks - end June. AR ready for Sept. Accounts shared LPC July meeting. Sent out for sign off by early August for min 30 days ahead Sept AGMs. | A | G
|  | Meet with Accountants Feb - May | Treasurers & FL | Accountant optional for 25-26 - have internal meeting both treasurers and FL and ZA | G | G
|  | Full governance review of banking processes to ensure governance robust | Exec & Finance Group | Reviewed November 2023 - Follow up Feb 2024 - incorporate into checklist going forward 2025-26 | G | G
|  | NHS / non levy monies monitored and utilised against MOU requirements | FL / Treasurers | Reviewed November 2023 - Follow up Feb 2024 - reviewed monthly and accounted for end of fianancial year | G | G
| Internal Governance | CPA and CPHW Joint Execs | Execs & ZA | Meeting Nov and Feb each year - alternate cost of venues etc | G | G
|  | CPE - LPC RAG status complete and follow actions annually | ZA / Exec | Awaiting Governance Documents and new RAG - draft seen January 2025 and action plan started | R | A
|  | New CPE Governance Documents Implementation | Execs & ZA | Review annually February / March | G | G
|  | Members capability & capacity & ways of working. | ZA / FL | Complete biannually and for new members - next due March - May 2025 | A | A
|  | Director Insurance & ICO and Employers Insurance and CPE insurance in place |  | In place | G | G
|  | Training & Conference attendance as needed - |  | CPE Conferences - Activity Courses, Pharma, CPPE | G | G
| Subgroups | Services / Exec and subgroups to operate at LPC Meetings - approve ToR and update as CPE advice comes through | All | ToR provisional in place - review Jan 2024 - then with new CPE governace packs - completed and keep under review | A | G
| Internal Communications | Ensure clear communications within Team and handovers for leave / cover – set up and review action logs. Ensure minutes of meetings are completed, checked and added to website as agreed in timely fashion | Team | Monday.com; Box documents, backup memory sticks, basic jobs confirmed | A | A
| Record keeping | Maintain version control of all documents in use and file in agreed location accessible to the team | Team | Default - admin Box - enter all final documents monthly. Share drives for documents requiring multiple access. Database maintained daily | G | A
| Risks & Issues | Maintain a log and follow up weekly, escalate as necessary. | ZA / Team | Action Log in place to add Escalated Risks Log - shared drive - using Monday.com | G | A
|  | Maintain record of stakeholder and contractor queries – use to inform best practice and FAQ support |  | Stakeholder mapping and database to be completed for March 2023. Completed but being added to as new people appointed. Decision on external meeting notes and actions handling | G | G
| SLAs - Services | Review all old & new SLAs & RAG plus hold quarterly meetings with local service commissioners. Website checks | EC / LNH | Review annually and when come up for renewal - in progress ahead of PNA | G | A
Work Strand | Subsection | Objective/ Desired Outcome | Lead
Contractor Support | Communications | website CPE format completed - annually check all pages for accuracy. All to be trained on how to maintain it by end April 2024 | SKS | Trained by end April 2024. Access to online training for whole team as needed. Regular review of website accuracy | A | G
|  | Social media - X / facebook / LinkedIn/ Blog | SKS | work to increase posts and blogs | G | G
|  | Communication Plan - all channels: General, PQS, PCNs, CPCF etc | Team | Formalise plan in 25-26, working om WhatsApp groups | A | A
|  | Newsletters - for AHW | Team | Biweekly general comms and bimonthly Service Comms | G | G
|  | Visits & Individual support & leadership training - set up visit and call cycle at some LPC meetings. Some targetting and agree key messaging | Team | To be reinstated - calls / visits in 2024 and to continue twice a year after LPC Meetings | A | G
| Training and development | Resources - Services pack update to one pagers | EC / LNH | External Pack to be completed and shared with stakeholders | A | A
|  | Events -2 a year min - 'don’t leave money on table' and make things simple - claiming guide etc | Team | Review option for series on tutorials online | A | A
|  | Recorded training bite size and Activity PDP |  | Review options for training - negotiating first one and media training when available | A | A
|  | Implementation & increased activity | EC / LNH | Review Data weekly / monthly - contact referrers or Contractors as needed | A | G
|  | Peer support - CPD revalidation | Team | Team / LPC where required | R | G
|  | New Contract / PQS / New Services - PCARP - resources | Team | PCARP main focus | G | G
Work Strand | Subsection | Objective/ Desired Outcome | Lead
| Local Service Commissioner meetings | arrange quarterly local commissioners and review SLA - to increase value | EC/ LNH |  | G | G
Stakeholder Management | Mapping & priorities (Healthcare, Social Care, Academia, Negotiating Bodies, Commissioners, Regulatory, Pharma, MP, Councillors, Third Sector, LMC, GP Federation, PCNs, patient bodies, charities, social prescribing) | National & Regional - relationships | FL |  | G | G
|  | Stakeholder mapping | EC / LNH/ FL / ZA | Maintain database and records | A | G
|  | Local - ICS, PLACE, PCN - meeting attendance and briefing documents / bids etc |  |  | G | G
|  | Local - CC, ICB NHSEi, CPCL - meeting attendance and briefing documents / bids etc |  |  | G | G
PCN Leads – CP and within PCN – support and link working - or any new links
| Communication Plan | Newsletters and packs for stakeholders including MPs | Team | Update and review and look at external newsletters | G | A
|  | Press & Media - to be proactive and utilise CPE resources | Team | 2-3 LPC Members to be meida trained | A | A
|  | Develop Marketing Plan | Team |  | A | G
| Engagement | Representation on appropriate groups | EC / FL | Need to be on PC Collaboratives, otherwise well represented | A | A
|  | Influencing & Negotiating at all levels (training as needed) | Team | Review PDPs for training needs | R | G
| Structure | Keep under review ICS mergers etc - if planned then consider merger LPCs | FL / Exec | Review annually | G | G
|  | Transformation work | FL | As required | G | G
| Digital | IT, databases, websites etc | SKS + Team | Daily / Weekly | G | G
| Reviewing plans/ strategies / journals | Collate summarise and disseminate information | LNH / EC / FL | Undertake annually April - June | R | R
| Patients | Healthwatch & Patient Communications | ZA / Team |  | G | G
Work Strand | Subsection | Objective/ Desired Outcome | Lead
Service & Pathway Opportunities Development | Essential Services | Support meeting core and resolution issues | Team |  | A | G
|  | DMS - support | Team |  | A | G
|  | PQS - support and communications | Team | No PQS 24-25 | R | R
| Advanced Services | NMS, CPCS, Flu, Covid, GPCPCS, EDCPCS, SS, BP, Pharmacy First, OC etc | EC / LNH | See main priorites below | G | G
| Locally Commissioned Services | Retention | LNH / EC |  | G | G
|  | Development add ons | EC / LNH | extended care decommissioned | A | A
| Data sets for meetings | Agree useful data to review quarterly and produce Services Report minimum alternate LPC Meetings | LNH / EC | Services Report alt LPC Meetings | A | G
| Opportunities | Understand priorities | EC / LNH |  | G | G
|  | Develop services and business cases - DES | EC / LNH |  | A | A
|  | Local - PCN - generic | EC / LNH | n/a CW | A | A
| Implementation | Services Pack to replace PCN pack | EC / LNH | Review annually in July | G | G
|  | New Services | EC / LNH |  | G | G
|  | National - local application | EC / LNH |  | G | G
| Working with CHS | Subcontracting, opportunity appraisals | EC / LNH |  | A | A
| Council | PH other services - generic | EC / LNH |  | A | A
| Project Management | Service work and data crunching and dissemination | LNH / EC | Work on local services data | A | A
Work Strand | LPC Plan Strategy | CPHW
| Workforce | Career, training, retention, cross sector - facilitation of information sharing | FL | Ongoing as needed | G | G
Local LPC Activities | Priorities - non BAU for 25-26 | PNA | All | See separate tab |  | G
|  | Self-Assessment |  | See separate tab |  | A
|  | Services related |  | See separate tab |  | A
|  | Transitions |  | See separate tab |  | A
|  | New CPCF |  | See separate tab |  | R
|  | LRCs |  | See separate tab |  | R
|  | NHS Plan 3 shifts |  | See separate tab |  | R
|  | Integration |  | See separate tab |  | G
| Local Relationships | Local - ICB, PLACE, PCN - meeting attendance and briefing documents / bids etc Local - CC, ICB, NHSEi - meeting attendance and briefing documents / bids etc | FL / EC / LNH | As arranged | G | G
|  | Issue resolution | ZA | As arranged
|  | Contractor – Stakeholder relationship support, intervention, | FL |  | G | G
|  | Develop network of Regional / Area Managers within Contractor base | ZA / Team | Include in biweekly comms | A | A
|  | Link to other Workforce / HCPs – Dentist / Optometrists for example | FL / EC | Annual meetings - LMC - more frequent | R | R
|  | CPCL New Leads – links into 8c role and digital transformation | FL / EC | Weekly meetings | G | G
|  | Network of patient groups and Pharma and third sector |  | Minimum annually | G | G
|  | Specialist Groups – eg Vaccinations / AMR etc | FL / EC | As arranged | G | G
HR | Clyde & Co templates in use | All in place and updated as needed - portal checked quarterly | FL / ZA | Quarterly check and update as necessary | G | G
| Objectives | Relate to Work plan areas and LPC priorities | FL for Team (Chair/ Exec for CEO) | Add priorites to work plan | G | G
| Reviews | Objective setting and annual review Jan - February ahead of joint Exec meeting. Interim reviews in Autumn ahead of November joint Exec meeting | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | A | G
| Training and development | PDP as part of Reviews / Interim Reviews | FL for Team (Chair/ Exec for CEO) | Winter and Autumn annually | A | G

## 2025-2026 Priorities
Priorities in addition to BAU Work Plan for 2025-2026 and beyond (set at January 2025 LPC)
Category | Activity | Lead | Outcomes Required | Budget - Levy Account or MOU Account - specify amount and source - estimates TBC | RAG | Q1 Update | Q2 Update | Q3 Update | Q4 Update
PNA | Review all PNAs in geography and border areas and feedback | FL / ZA | Full feedback on LPC area PNAs and key points for border ones especially looking at border pharmacies and impact on access | LPC Member time (Team within hours) - 5 days total for claims (1/2 day per PNA) - Levy account £5x300 = £1500
PNA | Ensure our PNAs have appropriate definitions of necessary vs desirable need vs want etc. | FL / ZA | Suitable definition based on reasonable geographical access, core hours and essential service provision but not advanced or local service provision - which can be managed by extending the range of services and number of pharmacies providing them as long as suffienciently well funded. Nor extended supplementary hours - any need can be managed by a commiddioned rota | n/a
Self-assessment LPC | Finance checklist | Exec | Use checklist to confirm all in place quarterly | n/a
Self-assessment LPC | Skills & Capacity | FL / ZA | Undertake our version annually which includes capacity | n/a
Self-assessment LPC | BAU LPC RAG | Gov Group | Complete self-assessment when final version available - twice a year | n/a
Services | PhF BP and OC Bundle | EC | Market and increase sign up and delivery to meet bundle and thresholds. Work on ABPM % | £3,000 from MOU
Services | Trasformation OOH | EC & FL | Build on the services proposal and accelerator sites to deliver more through CP in well funded services to support the left shift | £3,000 from MOU
Services | Local | EC | Full clarity of information on all services and quaterly meetings with commissioners and ultimate commissioners. Extended Care through OWM and ICB | £2,000 from Levy
Transition | CEO retirement - smooth transition in April - June 2026 | Transition Groups - Chair and VC of each LPC + FL | See transition group plan | £3,000 from Levy
Transition | Assess capacity of team, skills, flexibility and roles | CEO and Execs | See transition group plan & HR & Review outcomes | £1,200 from Levy
New CPCF | Actions following negotiations | All |  | £2,000 from Levy
New CPCF | Implementation of service changes / extensions | EC & Team |  | £2,000 from Levy + MOU £2,000
Integration CP into ICS | Local Vision and plans | All | Build on our list of service options and vision and strategy - to give focus on CP | £2000 - Levy
Integration CP into ICS | System Leadership links | FL | Build on Lynda and Charmaine relationships | £2,000 - MOU
Integration CP into ICS | Post Alison transition | FL & Exec | Develop a plan to maintain support | £1,000 - Levy
LRCs | Build relationship with the two LMCs | FL & Exec | Use Lisa to support links with LMC | £1,200 - Levy
NHS Plan 3 shifts | Analogue to digital | FL & AH & EC | Support use NHS App | £1,000 - MOU
NHS Plan 3 shifts | Left Shift Secondary - Primary | FL & AH & EC | Link into the OOH Transformation Programme locally - Lynda's work | £1,000 - MOU
NHS Plan 3 shifts | Treatment to Prevention | EC & Team | Build on work for local services with council and improve provision and range and viability | £1,200 - MOU or Levy